## Mob Plan
MNK - MOBILISATION
Go Live 29.06.2026
ITEM | WHO | % COMPLETE | Feb | March | April | May | May | May | w.c 01/06 | w.c 08/06 | w.c 15/06 | w.c 22/06 | w.c 29/06
Contract award announced | MNK | 100% | bar: Feb
MNK/Fika to agree mob plan | MNK / Fika | 100% | bar: Feb
Light equipment discussion and proposal | Fika / MNK | 100% | bar: Feb
Visit Lockhart Equipment Showroom to select light equipment | Fika / MNK | 100% | bar: Feb
Service agreement signed | MNK / Fika | 100% | bar: Feb to March
Agree full offering and service expectations | MNK / Fika | 100% | bar: Feb to March
Agree and sign off light equipment required for service delivery | MNK / Fika | 100% | bar: Feb to March
Agree Alchohol product list if required | MNK / Fika | 50% | bar: Feb to March
Uniform discussion | MNK / Fika | 100% | bar: March
Commence recruitment drive for on-site team | Fika | 100% | bar: May
Order Coffee machines, grinders, vending coffee machines and zip taps | Fika | 100% | bar: May
Building walk through and confirmation of service locations | Fika / MNK | 100% | bar: May
Agree on signage and communication (Menus/Tickets/Holders etc) | Fika / MNK | 50%
Establish booking protocols for hospitality | Fika / MNK | 50%
Installation and handover of equipment and training | Fika / MNK | 100%
Agree hospitality brochure and service costings | Fika / MNK | 0%
FIKA to register catering location with local authority | Fika | 0%
All supplier accounts to be set up | Fika | 0%
Music / Alcohol licences applied if required | Fika / MNK | 100%
MNK to provide passes for mobilisation team | MNK | 100%
Uniforms to be ordered and issued | Fika | 100%
Set up email account for location (mnk@fikacatering.com) | Fika | 100%
Purchase of IPAD for due diligence / Navitas | Fika | 100%
Purchase laptop | Fika | 100%
Purchase Toucan Eco | Fika | 100%
COSHH training with supplier | Fika | 100%
FIKA team to complete allergen training, certifications, fire procedures etc. | Fika | 0%
Coffee machine installed and commissioned | Fika | 100%
Staff induction / paperwork / payroll | Fika | 0%
Place orders for Barista Bar | Fika | 0%
Place order for cleaning chemicals | Fika | 100%
Opening location H&S audit | Fika | 0%
Review and complete risk assessments for all service areas | Fika | 0%
Train team on Allergen Policy/Customer Service/MNK Culture alignment | Fika | 0%
MNK to provide location specific policies around fire evacuation, equipment maintanance, pest control. etc | MNK / MNK | 0%
All dry store, coffee and beverage point products delivered to site and unpacked | Fika | 0%
Set up Beverage / Pantry Points | Fika | 0%
Cleaning products delivered to site and unpacked | Fika | 0%
LAUNCH WEEK | Fika / MNK | 0%
End of week 1 debrief | Fika / MNK | 0%

## QuestionsActions
MNK - MOBILISATION
Go Live End of April 2025 tbc
QUESTION | RESPONSE | DEADLINE | COMPLETE Y/N

## Notes
Site Address: | Level 20
110 Bishopsgate
London
EC2N4AY
Maximum height for van 3.5m
Open Y/N
Accounts to Open | Modern Standard
London Dairies
Jacksons
| Lockhart | Y
DDC Foods
Cakeheads
Bidfood
| Navitas | Y
County Supplies
Paul Rhodes
Liberty
Majestic
Nemi

## Servery Product List
Servery (Barista Bar)
Item - Fruit | Supplier | Proposed Selling Price
Bananas | County | Free Issue 50p | TUESDAY
Easy Peelers | County | Free Issue 50p
Pears | County | Free Issue 50p
Apples | County | Free Issue 50p
Kiwis | County | Free Issue 50p | flexible
Plums | County | Free Issue 50p | flexible
Item - Coffee
Espresso | Modern Standard | Free Issue £1.75
Macchiato | Modern Standard | Free Issue £1.75
Americano | Modern Standard | Free Issue £1.75
Latte | Modern Standard | Free Issue £1.75
Flat White | Modern Standard | Free Issue £1.75
Cappuccino | Modern Standard | Free Issue £1.75
Mocha | Modern Standard | Free Issue £1.75
Hot Chocolate | Modern Standard | Free Issue £1.75
Chai Latte | Modern Standard | Free Issue £1.75
Dirty Chai | Modern Standard | Free Issue £1.75
Item - Tea
English Breakfast (loose leaf) | Nemi | Free Issue £1.75
Earl Grey (loose leaf) | Nemi | Free Issue £1.75
Moroccan Mint (loose leaf) | Nemi | Free Issue £1.75
Super Berry (loose leaf) | Nemi | Free Issue £1.75
Sencha Green Tea (loose leaf) | Nemi | Free Issue £1.75
Lemon and Ginger (loose leaf) | Nemi | Free Issue £1.75
Item - Alternative Milk
Whole Milk | London Dairy | n/a | MONDAY
Skimmed Milk | London Dairy | n/a | MONDAY
Oat Milk | London Dairy | n/a | MONDAY
Coconut Milk | London Dairy | n/a | MONDAY
Item - Other
White Sugar Sticks | Bidfood | n/a
Brown Sugar Sticks | Bidfood | n/a
Sweetner | Bidfood | n/a
Item - Pastries
Item | Supplier | Case Qty | Price per case | Price per unit | Desired GP% | Inc. GP% | Inc. VAT | Suggested sell | Actual GP%
Croissant | Galeta | 1 |  | 1.26 | 40% | 2.1 | 2.52 | 2.1
Pain Au Chocolate | Galeta | 1 |  | 1.49 | 40% | 2.4833 | 2.98 | 2.4
Cinnamon bun | Galeta | 1 |  | 1.94 | 40% | 3.2333 | 3.88 | 2.75
Almon Croissant | Galeta | 1 |  | 1.89 | 40% | 3.15 | 3.78 | 2.95
Item - Cakes
Vegan Banana Cake | Galeta | 12 | 17.9 | 1.4917 | 30% | 2.131 | 2.5571 | 2.5 | 40.33%
Muffins | Galeta | 12 | 19.2 | 1.6 | 40% | 2.6667 | 3.2 | 2.5 | 36%
Salted Caramel Brownie | Galeta | 18 | 27.9 | 1.55 | 40% | 2.5833 | 3.1 | 2.5 | 38%
Matcha Raspberry Cookies | Galeta | 24 | 37.2 | 1.55 | 40% | 2.5833 | 3.1 | 2.95 | 47.46%
Item - Snacks
Propercorn (Lightly Sea Salted) | DDC | 24 | 16.36 | 0.68167 | 40% | 1.1361 | 1.3633 | 1 | 31.83%
Propercorn (Sweet and Salty) | DDC | 24 | 16.36 | 0.68167 | 40% | 1.1361 | 1.3633 | 1 | 31.83%
Fairfields Farm Crisps (Sweet Chilli) | DDC | 36 | 18.67 | 0.51861 | 40% | 0.86435 | 1.0372 | 1 | 48.14%
Fairfields Farm Crisps (Sea Salt and Vinegar) | DDC | 36 | 18.67 | 0.51861 | 40% | 0.86435 | 1.0372 | 1 | 48.14%
Olly's Olives (Chilli and Rosemary) | DDC | 12 | 14.88 | 1.24 | 40% | 2.0667 | 2.48 | 2.5 | 50.4%
Cambrook Nuts | DDC | 24 | 17.45 | 0.72708 | 40% | 1.2118 | 1.4542 | 1.5 | 51.53%
Proper Sea Salt Crunchy Corn | DDC | 12 | 12.44 | 1.0367 | 40% | 1.7278 | 2.0733 | 2 | 48.17%
Popchips (Various) | DDC | 24 | 21.17 | 0.88208 | 40% | 1.4701 | 1.7642 | 1.5 | 41.19%
Extra Gum | Bidfood | 30 | 11.99 | 0.39967 | 40% | 0.66611 | 0.79933 | 1 | 60.03%
Eat Natural (Various) | DDC | 12 | 10.73 | 0.89417 | 40% | 1.4903 | 1.7883 | 1.8 | 50.32%
Nakd Salted Caramel | DDC | 18 | 11.57 | 0.64278 | 40% | 1.0713 | 1.2856 | 1.3 | 50.56%
Nakd Peanut Delight | DDC | 18 | 11.57 | 0.64278 | 40% | 1.0713 | 1.2856 | 1.3 | 50.56%
Metcalfes Rice Cakes | DDC | 12 | 8.71 | 0.72583 | 40% | 1.2097 | 1.4517 | 1.45 | 49.94%
Urban Fruity Nut Mix | DDC | 20 | 13.33 | 0.6665 | 40% | 1.1108 | 1.333 | 1.4 | 52.39%
Emily Rainbow Roots Vegetable Snacks | Bidfood | 12 | 8.19 | 0.6825 | 40% | 1.1375 | 1.365 | 1.4 | 51.25%
Love Corn (45g) (BBQ) | Bidfood | 24 | 12.44 | 0.51833 | 40% | 0.86389 | 1.0367 | 1 | 48.17%
Bear Fruit Yoyo (Various) (No VAT) | DDC | 14 | 11.75 | 0.83929 | 40% | 1.3988 | 1.6786 | 1.7 | 50.63%
Protein Ball | Bidfood | 10 | 10.85 | 1.085 | 40% | 1.8083 | 2.17 | 2.25 | 51.78%
Item - Drinks |  |  |  |  | 40%
Coke Zero (can) | Bidfood | 24 | 15.44 | 0.64333 | 40% | 1.0722 | 1.2867 | 1 | 35.67%
Diet Coke (can) | Bidfood | 24 | 14.5 | 0.60417 | 40% | 1.0069 | 1.2083 | 1 | 39.58%
Sprite Zero (can) | Bidfood | 24 | 13.99 | 0.58292 | 40% | 0.97153 | 1.1658 | 1 | 41.71%
Fix8 Kombucha (various) (NO VAT) | DDC | 12 | 15.11 | 1.2592 | 40% | 2.0986 | 2.5183 | 2.5 | 49.63%
Innocent Juice (orange) | DDC | 8 | 11.26 | 1.4075 | 40% | 2.3458 | 2.815 | 2.85 | 50.61%
Vit Hit (various) | DDC | 12 | 11.6 | 0.96667 | 40% | 1.6111 | 1.9333 | 2 | 51.67%
Vita Coco | DDC | 12 | 11.54 | 0.96167 | 40% | 1.6028 | 1.9233 | 2 | 51.92%
Moju Shots (various) (NO VAT) | DDC | 18 | 24.76 | 1.3756 | 40% | 2.2926 | 2.7511 | 2.75 | 49.98%
Soho Sandwhich
coco de mama
wraps
etc.
Toast Station
White Tin Sliced | Paul Rhodes
Granary Tin Sliced | Paul Rhodes
Bagels Plain | Paul Rhodes
Tiger bloomer | Paul Rhodes

## Kitchenette Product List
Kitchenette / Pantry Product List
Item - Tea for Kitchenettes
English Breakfast (loose leaf) | Nemi
Earl Grey (loose leaf) | Nemi
Moroccan Mint (loose leaf) | Nemi
Super Berry (loose leaf) | Nemi
Sencha Green Tea (loose leaf) | Nemi
Lemon and Ginger (loose leaf) | Nemi
White sugar (sachet) | ?
Brown sugar (sachet) | ?
Sweetners (sachet) | ?
Item - For hospitality meeting rooms
Island Bakery Biscuits | DDC
Canbrook Smoked Almonds | DDC
Dried Fruit (or dried mango? | DDC

## First Orders
Supplier | Qty | Ordered | Delivered
Modern Standard | Q | Q | Q
Bloom Coffee | 1 x 12kg | TRUE | TRUE
Mascot For Vending Coffee | 1 x 12kg | TRUE | TRUE
Decaf | 1 x 500g bags (preground) | TRUE | TRUE
Chai | 1kg | TRUE | TRUE
Hot Chocolate | 1kg | TRUE | TRUE
Caramel Syrup | 1 | TRUE | TRUE
Hazelnut Syrup | 1 | TRUE | TRUE
Vanilla Syrup | 1 | TRUE | TRUE
Syrup pumps | 3 | TRUE | TRUE
Tea Brewers | 5 | TRUE | TRUE
Supplier | Qty | Ordered | Delivered
NEMI Tea | Q | Q | Q
English Breakfast | 500g loose leaf | TRUE | TRUE
Earl Grey | 500g loose leaf | TRUE | TRUE
Sencha | 500g loose leaf | TRUE | TRUE
Mint | 500g loose leaf | TRUE | TRUE
Lemon and Ginger | 500g loose leaf | TRUE | TRUE
Red Berry | 500g loose leaf | TRUE | TRUE
Glass display jars | 35
Labels for jars | 5 x 6 labels for each line